## Sheet1
Bug ID | Linked Test Case(s) | Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Status | Comments
BUG-001 | TC-007 | Price filter (Free) not applied | “Price: Free” filter still shows paid courses | 1. Search any keyword 2. Set Price: Free 3. Review results | Only free courses should be shown | Some paid courses appear | Major | Open | Search filtering
BUG-002 | TC-014 | Curriculum tab doesn’t expand | Clicking Curriculum doesn’t reveal lectures/modules | 1. Open course 2. Click Curriculum tab | All lectures/modules listed | Tab expands, but no content shows | Major | Open | Found on mobile
BUG-003 | TC-022 | Wishlist as logged-out doesn’t prompt | Clicking “Add to Wishlist” while logged out does nothing | 1. Log out 2. Click heart on course | Prompt to login/register | No response, no prompt | Major | Open | Session handling
BUG-004 | TC-027 | Password reset email not sent | Forgot Password form submits, but reset email never received | 1. Go to Forgot Password 2. Enter registered email | Receive reset email | No email arrives after 10 minutes | Major | Open | Gmail, Yahoo
BUG-005 | TC-030 | Mobile menu overlaps search box | On mobile, opening menu covers search input box | 1. Open Udemy on mobile 2. Tap menu icon 3. Check search | Search bar always accessible | Menu overlays and hides search | Minor | Open | UI/mobile issue
BUG-006 | TC-036 | Login error message unclear | Entering wrong password shows vague error message | 1. Go to Login 2. Enter invalid creds | User-friendly, actionable error | “Something went wrong” shown, no guidance | Minor | Open | Needs improvement
BUG-007 | TC-031 | Images missing alt text | Some icons/images lack descriptive alt text (accessibility) | 1. Inspect homepage images/icons | All images/icons have alt attributes | Some are missing or generic | Minor | Open | Accessibility issue
BUG-008 | TC-041 | Can view full syllabus as guest | Logged-out users can see full syllabus, not just preview/overview | 1. Log out 2. Visit course detail 3. Scroll to Curriculum | Only part/teaser visible to logged-out users | Entire curriculum visible | Major | Open | Data exposure risk